PERSON 3

Full-Stack Application, Integration & CHW Workflow

24-hour hackathon • Deliverable implementation plan • Source-aligned to Anemia Screening Hackathon Project Guide

Operating principle: fork-and-graft the existing RAHULPATEL2002/anemia-detection Flask application; do not rebuild the full stack from scratch.

# Mission

Own the runnable application and end-to-end integration. Fork and retain the existing Flask/Jinja2/Vanilla JavaScript scaffold, mobile-first capture workflow, persistence and PDF generation; connect real preprocessing/model outputs and deliver the CHW referral experience.

# Source-aligned requirements

Use RAHULPATEL2002/anemia-detection as the primary scaffold; retain Flask, mobile-responsive UI, rear-camera capture preference, image quality gate, database persistence and PDF report capability where functioning.

Expose a single end-to-end flow: patient/demographic entry → conjunctiva or fingernail capture/upload → image validation and normalization → inference → result/triage → history/referral PDF.

Display a visual inspection sequence: raw image → glare-corrected/normalized ROI and ITA badge → Grad-CAM when available.

Implement the guide’s Green/Yellow/Red triage cards, demographic-aware thresholds and referral slip, but label the system as a prototype and verify threshold logic with the team before presenting it as clinical guidance.

Do not rebuild as a native mobile app; the guide explicitly prioritizes the existing responsive web app.

# Work plan by time

| Window | Tasks | Deliverable / exit check |
| --- | --- | --- |
| H0–H2 | Fork/clone the primary repository; create a reproducible environment; run the baseline UI and /api/predict endpoint. Assign integration ownership and branch conventions. | App starts locally and a baseline flow is demonstrated or blocker logged. |
| H2–H4 | Inspect templates/static assets, app.py, image_validator.py, storage_utils.py and pdf_report.py. Agree API schema with Person 2 and preprocessing call with Person 1. | Integration contract and file ownership documented. |
| H3–H8 | Keep existing capture/upload, validation and storage working. Build/adjust patient intake fields, anatomical modality selection and result-page layout. | Working UI with mock response clearly labelled as mock during development. |
| H6–H12 | Implement a service adapter that calls Person 1’s normalization and Person 2’s inference without embedding model logic in route handlers. Add timeouts/errors and useful messages. | Backend can call the shared pipeline; invalid-image path works. |
| H8–H15 | Implement result presentation: Hb estimate if genuinely available, probability/classification, quality warnings, raw/normalized preview and Grad-CAM if returned. | Result screen connected to real outputs or clearly marked fallback. |
| H12–H18 | Implement Green/Yellow/Red referral workflow, demographic inputs, referral status and SQLite persistence; update PDF to include patient/scan ID, result, uncertainty/limitations and referral destination. | Patient history and downloadable referral PDF work end-to-end. |
| H17–H20 | Add evaluation/analytics view for actual model metrics supplied by Person 2; show dataset/split provenance and stratified results only if available. | Metrics page uses real evaluation artifacts, not hardcoded claims. |
| H20–H22 | Integration freeze; test normal and failure paths, fresh app start, file upload/camera flow, persistence and PDF generation. | Release candidate; no mock values in production/demo path unless explicitly labelled. |
| H22–H24 | Prepare stable demo dataset/images, deployment/local fallback, short demo script and presentation flow. Avoid last-minute framework changes. | Repeatable demo from clean start. |

# Implementation checklist

Preserve existing routes and schema where practical; adapt the scaffold instead of replacing it.

Keep the prediction service behind one adapter so the app can switch from a mock to real inference without rewriting the UI.

Persist a scan ID, timestamp, anatomical modality, model output, quality warnings, referral status and generated report reference as supported by the existing storage layer.

Show model limitations and recommend confirmatory clinical testing; do not state that a smartphone image definitively diagnoses anemia.

Do not hardcode model metrics, calibration values, patient data or Hb values into the production path.

Use safe handling for personal data; for the demo, use synthetic/demo patient details unless real consent and authorization are in place.

# Suggested result-screen fields

| Section | Content |
| --- | --- |
| Capture | Patient/scan identifier, age and relevant demographic inputs, selected body part, image-quality status. |
| Image pipeline | Raw image, normalized ROI, ITA/feature metadata when available, Grad-CAM when available. |
| Model result | Hb estimate in g/dL only if returned by the regression model; anemia probability/classification; calibration status and warning. |
| Triage | Green/Yellow/Red workflow state based on verified rules; referral recommendation and status. |
| Report/history | Saved scan history and downloadable CHW referral PDF; clearly marked prototype/confirmatory-test note. |

# Dependencies and handoffs

| Needs from | Need | Provide to |
| --- | --- | --- |
| Person 1 | Callable preprocessing module, metadata fields and preview images. | Person 1: UI needs for visual inspection and invalid-image behavior. |
| Person 2 | Stable inference callable/endpoint, output schema, metrics and explanation artifacts. | Person 2: actual UI display constraints and integration failures. |

# Acceptance criteria

A user can complete the core flow from image capture/upload to a saved result and PDF from a clean application start.

The app handles invalid image, unavailable model, missing output and PDF/database errors without crashing.

Any mock/fallback output is explicitly labelled and cannot be mistaken for a genuine model prediction.

The UI is mobile-responsive and retains the base scaffold’s key functionality.

# Definition of done and handoff

Commit working code to the agreed branch and include a short README section with setup/run instructions.

Provide one reproducible test or example input and record observed output; never label mock output as a real model result.

Tell the integration owner what is implemented, what is incomplete, known limitations, and exact files changed.

Do not claim clinical diagnostic performance without evaluation against laboratory-measured hemoglobin and a leakage-safe test set.

# Scope guardrails from the source guide

Do not build a native Android/iOS app; use the existing mobile-responsive web application.

Do not train U-Net/Mask R-CNN from scratch, attempt INT4 quantization, train GAN/diffusion augmentation, or deploy PyTorch inference as Vercel serverless functions.

Treat dual-modality eye+nail fusion, the high-sensitivity toggle, leakage audit badge, and PWA as stretch goals only after the end-to-end core works.

The system is a screening aid/prototype, not a substitute for confirmatory CBC testing or professional clinical judgment.